## MOP
SGS INFRACON
Krisumi Corporation Pvt. Ltd.
Work Order No. & Date :- |  | RA-01 | Date: 08-05-2024
NAME OF CLIENT : Krisumi Corporation Pvt. Ltd.
Address: Sector 36A, Village Sihi and Harsaru , Gugram-Manesar Urban Complex, Tehsil and District Gurugram, Gurgaon Haryana-122004
GSTIN : 06AAECV0565A1ZR
State Code : 06 (Haryana)
PAN No.: AAECV0565A
Name of Project : Waterfall Residences
NAME OF CONTRACTOR : SGS INFRACON
GST NO:-06ADIFS9543H1ZO
State Code : 06 (Haryana)
S. No. | Description | Prev. Bill | This Bill | Total Amount
A | Work done
A1 | Value of work done |  | 4222450.145 | 4222450.145
A2 | Extra & additional work
A3 | Basic rate Diffrence
Gross Work Done (A=A1+A2+A3)
B | GST
B1 | CGST @9% | 0 | 380020.5131 | 380020.5131
B2 | SGST @9% | 0 | 380020.5131 | 380020.5131
Sub Total (B=B1+B2)
C | Total (C=A+B) | 0 | 4982491.1711 | 4982491.1711
D | Recoveries/ Tax Deductions
D1 | Performance Guarantee @ 5% on A(submitted)
D2 | Electrical Debit
D3 | TDS @ 2% on A | 0 | 84449.0029 | 84449.0029
D4 | Mobilization Advance
D5 | Safety Violation Penalty
| Sub Total (D=D1+D2+D3+D4) | 0 | 84449.0029 | 84449.0029
E | Total( E=C-D) | 0 | 4898042.1682 | 4898042.1682
Authorised Signatory |  |  | Authorised Signatory
SGS INFRACON |  |  | Krisumi Corporation Ltd.

## Abstract
BOQ FOR NEW PARKING,Miscellaneous Plumbing and rain water harvesting pit Work , KRISUMI, SEC-36A, GURUGRAM
|  | UOM | Qty | Rate | Amount | Qty. |  |  | Amount
[6 empty] | Previous | This | Cumulative | Previous | This | Cumulative
1 | Cutting, Filling , dressing with compaction up to 300 mm Depth with selected, suitable excavated earth already available at site in as directed by the Project Manager , and consolidating deposited layer by mechanical means, ramming and watering as per specifications including re-excavation, transportation, loading, unloading, carriage to dumping spot and all incidentals at all depth, levels, leads and lifts complete. | Sqm | 6829 | 25 | 170725 |  |  | 6828.73 | 0 | 170718.25 | 170718.25
[9 empty] | 0 | 0 | 0
2 | Providing and laying in position ready mixed plain cement concrete, with cement content as per approved design mix and manufactured in fully automatic batching plant and transported to site of work in transit mixer for all leads, having continuous agitated mixer, manufactured as per mix design of specified grade for plain cement concrete work, including pumping of R.M.C. from transit mixer to site of laying and curing, including the cost of centering, shuttering and finishing, including cost of curing, admixtures in recommended proportions as per IS : 9103 to accelerate/ retard setting of concrete, improve workability without impairing strength and durability as per direction of the Engineer-in-charge. | [7 empty] | 0 | 0 | 0
2.1 | M-10 grade plain cement concrete | Cum | 730 | 5100 | 3723000 |  |  | 722.873 | 0 | 3686652.3 | 3686652.3
Etra Item | [8 empty] | 0 | 0 | 0
2.2 | Extra and above Item no 2.1 fom M-15 grade plain cement Concrete | Cum | 730 | 185 | 135050 |  |  | 722.873 | 0 | 133731.505 | 133731.505
2.3 | Extra and above Item no 2.2 for placing of channels and broom finish of concrete | Cum | 730 | 150 | 109500 |  |  | 722.873 | 0 | 108430.95 | 108430.95
2.3 | Providing and laying of polythene sheet as per direction of Engineer-in-charge. | Sqm | 6829 | 18 | 122922 |  |  | 6828.73 | 0 | 122917.14 | 122917.14
3 | Rain Water Dewatering Pumps | [7 empty] | 0 | 0 | 0
a | Supply, installation, testing, commissioning and handing over of SUBMERSIBLE PUMP Flow-400 LPM Head- 15 meter approx 2.5 Hp, 2850 rpm, 3 Phase MOC- Casing- CI, Impeller- Grey Iron & shaft - SS410 Solid Passage- 20mm., complete in alrespect, pipe,cable,safety wire,tee,elbow,bend,flanges,stand for panels, etc required to complet the job as per site and as per direction of Engineer-In-Charge. 1 Set= ( 1W) Make:- CRI/Lubi/Kirloskar | Set | 1 | 38000 | 38000 |  |  |  | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
b | Supply, installation, testing, commissioning and handing over of DOL starter feeders of 2.5 HP approx capacity each comprising of incomer 16Amp TP MPCB with fixed neutral link, necessary contactors, start stop buttons, ON/OFF trip indicating lights, overload relays, single phase preventor, phase reversal, Ammeter including all necessary auxillary wiring and colour coded power wiring as required. 1 Set= ( 1W) Make:- L& T/Equivalent. | Set | 1 | Included in Item no 3 (a) |  |  |  |  | 0
[9 empty] | 0 | 0 | 0
c | Supply, installation, testing, commissioning and handing over of 4Cx4sqmm Copper flexible cable including conduit complete in alrespect as per site and as per direction of Engineer-In-Charge. Make:- Polycab/KEI | M | 50 | 450 | 22500 |  |  |  | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
d | Supply, installation, testing, commissioning and handing over of 110 mm dia. UPVC-6 KG/CM2 IS-4985 pipe for rain water dewatering pumps complete in alrespect like tee,elbow,bend etc. required to complet the job as per site and as per Engineer-In- Charge.. Make:- Supreme/Astral/Ajay | M | 30 | 1120 | 33600 |  |  |  | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
e | Constructing brick masonry rain water hodling tank size 2x1.5x 2 M of cement mortar 1:4 (1 cement : 4 coarse sand) R.C.C. top slab with 1:2:4 mix ( 1cement : 2 coarse sand : 4 graded stone aggregate 20 mm nominal size ), foundation concrete 1:4:8 mix (1cement : 4 coarse sand : 8 graded stone aggregate 20 mm nominal size) inside plastering 12mm thick with cement mortar 1:3 (1 cement : 3 coarse sand) finished with floating coat of neat cement and making necessary channels in cement concrete 1:2:4 (1 cement : 2 coarse sand : 4 graded stone aggregate 20mm nominal size) finished with a floating coat of neat cement and footrest as required to complete as per standard design. | Nos | 1 | 70000 | 70000 |  |  |  | 0 | 0 | 0
4 | External Plumbing Work For Drivers Cabin | [7 empty] | 0 | 0 | 0
A | Water Supply | [7 empty] | 0 | 0 | 0
1 | Providing and fixing Chlorinated Polyvinyl Chloride (CPVC) SDR-11 pipes, having thermal stability for hot & cold water supply, including all CPVC plain & brass threaded fittings, including fixing the pipe with clamps at 1.00 m spacing. This includes jointing of pipes & fittings with one step CPVC solvent cement and testing of joints complete as per direction of Engineer in Charge.Internal work - for Inlet of tank and outlet Make:- Ajay/Astral/Supreme | [7 empty] | 0 | 0 | 0
i | 25 mm dia nominal bore | Metre | 40 | 180 | 7200 |  |  |  | 0 | 0 | 0
ii | 32 mm dia nominal bore | Metre | 80 | 210 | 16800 |  |  |  | 0 | 0 | 0
2 | Providing & fixing full way lever operated forged brass ball valve of brass body with forged brass hard chrome plated steel ball tested to a pressure not less than 10 Kg / sqcm with threaded / flanged joints complete with nuts, bolts, gaskets, washers etc. Make:- Zoloto/Sant | [7 empty] | 0 | 0 | 0
i | 25 mm dia. | Nos | 2 | 550 | 1100 |  |  |  | 0 | 0 | 0
ii | 32 mm dia. | Nos | 2 | 640 | 1280 |  |  |  | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
3 | Providing and placing on MS structure three layer 500 Ltrs. LLDPE polyethylene water storage tank ISI marked with cover and suitable locking arrangement and making necessary holes for inlet, outlet, valves, union and overflow pipes with fittings, nippplse and the base support for tank. Make:- Sintex/Plasto/Sheetal | Nos | 1 | 8500 | 8500 |  |  |  | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
| Supply, Fixing of MS structure work for over head water storage tank capacity 500 Ltrs with black enamle paints and etc. required to complete in alrespect as per site conditions.. Make:- Tata/Jindal. | Kg | 500 | 120 | 60000 |  |  |  | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
B | Sewerage & Driange | [7 empty] | 0 | 0 | 0
1 | Excavating trenches of required width for pipes, etc including excavation for sockets, and dressing of sides, ramming of bottoms, depth up to 1.m including getting out the excavated soil, and then returning the soil as required, in layers not exceeding 20 cm in depth including consolidating each deposited layer by ramming, watering, etc. and disposing of surplus excavated soil as directed, within a lead of 50m Pipes, cables etc. exceeding 80mm dia. But not exceeding 300mm dia. | Metre | 30 | 150 | 4500 |  |  |  | 0 | 0 | 0
2 | Providing and laying pressure agriculture -6 kg/cm2- IS -4985 pipe pipeswith uPVC pipe fittings e.g. elbows, tees, reducers, unions, plugs, flanges etc. and clamps and jointing with solvent cement including chase cutting and making good the walls etc. wherever required for waste connection from external sewerage. Make: Ajay/Astral/Supreme | [7 empty] | 0 | 0 | 0
i | 110 mm dia | Metre | 10 | 970 | 9700 |  |  |  | 0 | 0 | 0
ii | 150 mm dia | Metre | 30 | 1850 | 55500 |  |  |  | 0 | 0 | 0
3 | Providing and laying cement concrete 1:5:10 (1 cement : 5 coarse sand : 10 graded stone aggregate 20 mm nominal size) up to haunches of sewerage pipes including bed concrete as per standard design : | [7 empty] | 0 | 0 | 0
i | 150 mm dia | Metre | 30 | 700 | 21000 |  |  |  | 0 | 0 | 0
4 | Constructing brick masonry manhole cement mortar 1:4 (1 cement : 4 coarse sand) R.C.C. top slab with 1:2:4 mix ( 1cement : 2 coarse sand : 4 graded stone aggregate 20 mm nominal size ), foundation concrete 1:4:8 mix (1cement : 4 coarse sand : 8 graded stone aggregate 20 mm nominal size) inside plastering 12mm thick with cement mortar 1:3 (1 cement : 3 coarse sand) finished with floating coat of neat cement and making necessary channels in cement concrete 1:2:4 (1 cement : 2 coarse sand : 4 graded stone aggregate 20mm nominal size) finished with a floating coat of neat cement complete as per standard design. | [7 empty] | 0 | 0 | 0
i | Inside size 45 x 45 cm and 50 cm deep including SFRC cover with frame (light duty). With F.P.S. bricks with class designation 75 | Nos | 6 | 9500 | 57000 |  |  |  | 0 | 0 | 0
5 | Extra depth for manholes Size 45 x 45 cm (With With F.P.S. bricks with class designation 75) | Metre | 1 | 2000 | 2000 |  |  |  | 0 | 0 | 0
6 | Providing and fixing square-mouth S.W. gully trap class SP-1 complete with C.I. grating brick masonry chamber with water tight SFRC cover with frame of 300 x300 mm size (inside) as per standard design: 100x100 mm size P type With common burnt clay F.P.S. (non modular) bricks of class designation 7.5 | Each | 6 | 8000 | 48000 |  |  |  | 0 | 0 | 0
7 | Constructing brick masonry septic tank size 2x1.5x 2 M including soakpit of size-1.5x1.5 meter of cement mortar 1:4 (1 cement : 4 coarse sand) R.C.C. top slab with 1:2:4 mix ( 1cement : 2 coarse sand : 4 graded stone aggregate 20 mm nominal size ), foundation concrete 1:4:8 mix (1cement : 4 coarse sand : 8 graded stone aggregate 20 mm nominal size) inside plastering 12mm thick with cement mortar 1:3 (1 cement : 3 coarse sand) finished with floating coat of neat cement and making necessary channels in cement concrete 1:2:4 (1 cement : 2 coarse sand : 4 graded stone aggregate 20mm nominal size) finished with a floating coat of neat cement complete as per standard design. | Each | 1 | 150000 | 150000 |  |  |  | 0 | 0 | 0
| Total Amount * excl GST |  |  |  | 4867877 |  |  |  | 0 | 4222450.145 | 4222450.145

## Parking MB
Contractor -SGS Infracon
Client - Krisumi corporation
Project - Parking Area
RA BILL
Period-
Measurement Book :- Parking Area
Item No. | Location / Description | Grid | Unit | Nos. | Length | Width | Height | % Release | Quantity | Remarks
1 | Cutting, Filling , dressing with compaction up to 300 mm Depth with selected, suitable excavated earth already available at site in as directed by the Project Manager , and consolidating deposited layer by mechanical means, ramming and watering as per specifications including re-excavation, transportation, loading, unloading, carriage to dumping spot and all incidentals at all depth, levels, leads and lifts complete.
| Parking Area as per cadd |  | SQM |  | 6828.73 |  |  | 100% | 6828.73
| Grand TOTAL QTY. (A) | [7 empty] | 6828.73 | SQM
| Quantity paid previous | [8 empty] | SQM
| Quantity for this bill | [7 empty] | 6828.73 | SQM
2 | Providing and laying in position ready mixed plain cement concrete, with cement content as per approved design mix and manufactured in fully automatic batching plant and transported to site of work in transit mixer for all leads, having continuous agitated mixer, manufactured as per mix design of specified grade for plain cement concrete work, including pumping of R.M.C. from transit mixer to site of laying and curing, including the cost of centering, shuttering and finishing, including cost of curing, admixtures in recommended proportions as per IS : 9103 to accelerate/ retard setting of concrete, improve workability without impairing strength and durability as per direction of the Engineer-in-charge.
2.1 | M-10 grade plain cement concrete
| Parking Area as per cadd |  | cum |  | 6828.73 |  | 0.1 | 100% | 682.873
|  |  | cum |  | 400 |  | 0.1 | 100% | 40
| Grand TOTAL QTY. (A) | [7 empty] | 722.873 | Cum
| Quantity paid previous | [8 empty] | Cum
| Quantity for this bill | [7 empty] | 722.873 | Cum
2.2 | Extra and above Item no 2.1 fom M-15 grade plain cement Concrete
| Parking area |  | cum |  | 6828.73 |  | 0.1 | 100% | 682.873
|  |  | cum |  | 400 |  | 0.1 | 100% | 40
| Grand TOTAL QTY. (A) | [7 empty] | 722.873 | Cum
| Quantity paid previous | [8 empty] | Cum
| Quantity for this bill | [7 empty] | 722.873 | Cum
2.3 | Extra and above Item no 2.2 for placing of channels and broom finish of concrete
| Parking area |  | cum | 1 | 6828.73 |  | 0.1 | 100% | 682.873
|  |  | cum |  | 400 |  | 0.1 | 100% | 40
| Grand TOTAL QTY. (A) | [7 empty] | 722.873 | Cum
| Quantity paid previous | [8 empty] | Cum
| Quantity for this bill | [7 empty] | 722.873 | Cum
2.4 | Providing and laying of polythene sheet as per direction of Engineer-in-charge.
| Parking area |  | cum | 1 | 6828.73 |  |  | 100% | 6828.73
| Grand TOTAL QTY. (A) | [7 empty] | 6828.73 | SQM
| Quantity paid previous | [8 empty] | SQM
| Quantity for this bill | [7 empty] | 6828.73 | SQM